## Legend
AstraWMS Requirements Traceability Matrix
Source | AstraWMS Scope & Solution Definition v1.0 (docs/scope/*.md), baseline 2026-09-30. Every requirement ID, exception code and interface ID in the document set is one row on the RTM sheet.
How to use | Maintain only the yellow-header columns on the RTM sheet (Fit-Gap Disposition, Design Reference, Test Status, Defect ID(s), Owner). Summary recalculates automatically. Add further test cases for a requirement as extra rows with the same Req ID and TC suffix -02, -03 …
Column | Meaning
Req ID | Identifier from the scope documents: <AREA>-<NNN> requirement, <AREA>-EX-<NN> exception flow, IF-<FLOW>-<NNN> ERP interface.
Type | Requirement ¦ Exception ¦ Interface.
Area / Section / Source Document | Functional area (from the ID prefix), the heading it appears under, and the Markdown file that defines it.
Requirement / Exception | Requirement text, exception name, or interface object/direction/trigger as written in the scope.
Acceptance Criteria | Rules: enforced as stated (positive + negative case). Exceptions: detection, resolution and ERP impact from the exception table. Interfaces: SAP/Oracle technology, design peak volume and latency SLA. HA/DR NFRs: the stated target.
Priority | MoSCoW: M Must, S Should, C Could, W Won't (document §0.4).
Fit-Gap Disposition (input) | Blueprint outcome (§I.1.2): Fit - Standard, Fit - Configuration, Gap - Extension, Gap - Process Change, Rejected, Deferred.
Design Reference (input) | Process Design Document (PDD) or Interface Specification Document (ISD) reference.
Test Case ID | Generated placeholder TC-<ReqID>-01; replace/extend with IDs from the test management tool.
Test Type / Test Phase | Proposed from the Testing Strategy (§I.2): functional, exception, integration, interface, performance, resilience/DR, security & audit, automation, regulated validation.
Test Status (input) | Not Started, In Progress, Passed, Failed, Blocked, Deferred, N/A.
Example (filled row) | Req ID INB-002 · Fit-Gap Disposition: Fit - Configuration · Design Reference: PDD-INB-01 §3.2 · Test Status: Passed · Defect ID(s): DEF-0142 (closed) · Owner: Receiving Process Owner
Assumptions
A1 | Exception codes carry no priority in the scope; they are set to M because §I.2 requires every exception code to be covered by a test case.
A2 | NFR-020 to NFR-030 (HA/DR) list a target instead of a priority; they are set to M.
A3 | Interfaces IF-* are set to M; drop to S/C per site if an interface is not used (e.g. kitting IF-KIT-001 at sites without kitting).
A4 | Where a priority carries a qualifier (e.g. 'M (if sorter in scope)'), the letter is used and the qualifier is kept in Notes.
A5 | Test Type and Phase are proposals derived from the requirement wording (latency/throughput targets → Performance; e-signature/Part 11 → Regulated validation). Confirm during test planning.
Coverage gap | Tables without requirement IDs are not in the RTM: §E.4 Security & Compliance, §E.6 API Governance, §D.5 Integration Security, §G.2 Web UI modules, §H KPI definitions and reports. Assign IDs in the scope document to trace them.

## Summary
AstraWMS: Requirements Traceability Summary
All figures are formulas over the RTM sheet and update as Test Status / Fit-Gap Disposition are maintained.
Area | Total Items | Requirements | Interfaces | Exceptions | Must (M) | Should (S) | Could (C) | Fit-Gap Assessed | Passed | Failed / Blocked | In Progress | Not Started | % Passed | % Fit-Gap Assessed
Inbound
Putaway & Storage
Outbound Order Mgmt
Picking
Packing, Staging & Shipping
Inventory Management
Replenishment
Returns
Cross-Docking
Value-Added Services
Kitting / Light Mfg
Quality Management
Multi-WH & 3PL
Cold Chain & HazMat
Advanced Features
ERP Integration
ERP Interfaces
Non-Functional
TOTAL
Check: RTM row count

## RTM
Req ID | Type | Area | Section | Source Document | Requirement / Exception | Acceptance Criteria / Expected Behaviour | Priority | Fit-Gap Disposition | Design Reference | Test Case ID | Test Type | Test Phase | Test Status | Defect ID(s) | Owner | Notes
INB-001 | Requirement | Inbound | 1.3 System Rules | docs/scope/02-functional-inbound-storage.md | Receipt against an expectation must validate the item against the expectation lines. Unexpected items are blocked unless the user holds INB_RECEIVE_UNEXPECTED. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INB-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INB-002 | Requirement | Inbound | 1.3 System Rules | docs/scope/02-functional-inbound-storage.md | Over-receipt tolerance is configurable per vendor, item class, and warehouse, as % and absolute units. Exceeding it requires supervisor override with a reason code. The default mirrors the ERP PO over-delivery tolerance (SAP UEBTO, Oracle QTY_RCV_TOLERANCE). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INB-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INB-003 | Requirement | Inbound | 1.3 System Rules | docs/scope/02-functional-inbound-storage.md | Under-receipt: a receipt may close short. The residual is reported back so the ERP can adjust the delivery or leave the PO open, as configured per flow. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INB-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INB-004 | Requirement | Inbound | 1.3 System Rules | docs/scope/02-functional-inbound-storage.md | Expiry validation: reject or hold when remaining shelf life < the item's *minimum remaining shelf life on receipt* (SAP MHDRZ; Oracle shelf-life days). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INB-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INB-005 | Requirement | Inbound | 1.3 System Rules | docs/scope/02-functional-inbound-storage.md | Lot uniqueness: the same lot number for the same item from different vendors is allowed; the system key is (item, lot, vendor-lot). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INB-005-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INB-006 | Requirement | Inbound | 1.3 System Rules | docs/scope/02-functional-inbound-storage.md | Serial capture: for serial-controlled items the count of serials must equal the received quantity in base UoM; duplicate serials within the item are rejected. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INB-006-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INB-007 | Requirement | Inbound | 1.3 System Rules | docs/scope/02-functional-inbound-storage.md | Catch weight: for catch-weight items, capture actual weight per case or per pallet within tolerance (±x%) of nominal. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-INB-007-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INB-008 | Requirement | Inbound | 1.3 System Rules | docs/scope/02-functional-inbound-storage.md | Receipt date and time are stamped in site local time and UTC; the GR posting date follows ERP period rules (no posting into a closed period; next-open-period logic). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INB-008-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INB-009 | Requirement | Inbound | 1.3 System Rules | docs/scope/02-functional-inbound-storage.md | Door assignment respects temperature class, HazMat door restrictions, and door equipment (leveller, dock lock). | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-INB-009-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INB-010 | Requirement | Inbound | 1.3 System Rules | docs/scope/02-functional-inbound-storage.md | Appointment no-show: auto-release the slot after N minutes past the slot start; the carrier scorecard is updated. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-INB-010-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INB-011 | Requirement | Inbound | 1.3 System Rules | docs/scope/02-functional-inbound-storage.md | ASN SSCC receipt must be a *single-scan* confirmation for a homogeneous pallet; mixed pallets require line-level verification, or ASN trust mode per vendor (trusted vendors can skip line-level verification). | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-INB-011-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INB-012 | Requirement | Inbound | 1.3 System Rules | docs/scope/02-functional-inbound-storage.md | Dock-to-stock timer starts at unload scan and ends at putaway confirmation. The timer is visible on the dashboard; an SLA breach raises an alert. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-INB-012-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INB-EX-01 | Exception | Inbound | 1.5 Exception Handling | docs/scope/02-functional-inbound-storage.md | Seal mismatch or broken | Detection: Seal scan ≠ ASN seal ¦ Resolution: Hold trailer; photo capture; supervisor decides to accept (record) or reject (trailer refused) ¦ ERP impact: None until receipt; claim flagged | M |  |  | TC-INB-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INB-EX-02 | Exception | Inbound | 1.5 Exception Handling | docs/scope/02-functional-inbound-storage.md | Over-receipt beyond tolerance | Detection: Qty validation ¦ Resolution: Supervisor override (reason) or receive excess into OVERAGE status location pending buyer decision ¦ ERP impact: ERP PO increase or return-to-vendor | M |  |  | TC-INB-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INB-EX-03 | Exception | Inbound | 1.5 Exception Handling | docs/scope/02-functional-inbound-storage.md | Short receipt | Detection: Receipt closed < expected ¦ Resolution: Reason code (vendor short, damaged, in transit); auto-generate vendor discrepancy report (EDI 861 optional) ¦ ERP impact: Delivery quantity adjusted; PO remains open or closed per config | M |  |  | TC-INB-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INB-EX-04 | Exception | Inbound | 1.5 Exception Handling | docs/scope/02-functional-inbound-storage.md | Damaged goods | Detection: User flags damage ¦ Resolution: Received into DAMAGED status; photo evidence; creates claim record; route to damage cage ¦ ERP impact: GR to blocked stock (SAP stock type S; Oracle hold status) | M |  |  | TC-INB-EX-04-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INB-EX-05 | Exception | Inbound | 1.5 Exception Handling | docs/scope/02-functional-inbound-storage.md | Unknown item or GTIN not in master | Detection: Scan resolution fails ¦ Resolution: Item placed in UNKNOWN holding location; master data request to ERP; auto-retry mapping when the master arrives ¦ ERP impact: None until resolved | M |  |  | TC-INB-EX-05-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INB-EX-06 | Exception | Inbound | 1.5 Exception Handling | docs/scope/02-functional-inbound-storage.md | Expiry below minimum | Detection: INB-004 ¦ Resolution: Reject (refuse at dock) or receive to QI for QA decision ¦ ERP impact: Blocked or QI stock | M |  |  | TC-INB-EX-06-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INB-EX-07 | Exception | Inbound | 1.5 Exception Handling | docs/scope/02-functional-inbound-storage.md | ASN SSCC not found / duplicate SSCC | Detection: SSCC lookup ¦ Resolution: Convert to line-level receipt; relabel with WMS LPN ¦ ERP impact: None | M |  |  | TC-INB-EX-07-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INB-EX-08 | Exception | Inbound | 1.5 Exception Handling | docs/scope/02-functional-inbound-storage.md | Lot/serial mismatch with ASN | Detection: Attribute validation ¦ Resolution: Accept actual lot (ERP batch created by message) or hold, per vendor rule ¦ ERP impact: Batch creation (SAP BATMAS/BAPI_BATCH_CREATE) | M |  |  | TC-INB-EX-08-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INB-EX-09 | Exception | Inbound | 1.5 Exception Handling | docs/scope/02-functional-inbound-storage.md | Receipt with no expectation (blind) | Detection: No ASN ¦ Resolution: Permission-controlled; creates unplanned receipt; ERP document requested/created by inbound message ¦ ERP impact: ERP creates inbound delivery / unordered receipt | M |  |  | TC-INB-EX-09-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INB-EX-10 | Exception | Inbound | 1.5 Exception Handling | docs/scope/02-functional-inbound-storage.md | Temperature excursion on arrival | Detection: Reefer reading outside range ¦ Resolution: Hold entire load; QA notification; §14 cold-chain flow ¦ ERP impact: QI stock | M |  |  | TC-INB-EX-10-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INB-EX-11 | Exception | Inbound | 1.5 Exception Handling | docs/scope/02-functional-inbound-storage.md | ERP change after receipt started | Detection: Delivery update message for an IN_PROGRESS expectation ¦ Resolution: Change queued; supervisor must accept/reject; qty reduction below the received qty is rejected back to ERP ¦ ERP impact: Error reply to ERP | M |  |  | TC-INB-EX-11-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
PUT-001 | Requirement | Putaway & Storage | 2.4 System Rules | docs/scope/02-functional-inbound-storage.md | Compatibility filters (temperature, HazMat segregation, bonded, owner segregation) are hard constraints; overrides are impossible for any role. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-PUT-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PUT-002 | Requirement | Putaway & Storage | 2.4 System Rules | docs/scope/02-functional-inbound-storage.md | Scan of location check digit required to confirm. Alternate location override requires permission PUT_OVERRIDE and is validated against PUT-001 plus capacity. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-PUT-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PUT-003 | Requirement | Putaway & Storage | 2.4 System Rules | docs/scope/02-functional-inbound-storage.md | Multi-LPN putaway: an operator may carry up to N LPNs (per equipment type); the system sequences drops by optimal route. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-PUT-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PUT-004 | Requirement | Putaway & Storage | 2.4 System Rules | docs/scope/02-functional-inbound-storage.md | Partial putaway: the operator may split an LPN when the target is full; the remainder gets a new task. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-PUT-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PUT-005 | Requirement | Putaway & Storage | 2.4 System Rules | docs/scope/02-functional-inbound-storage.md | Putaway to QI locations only for QI-status stock; available stock cannot be put into QC zones. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-PUT-005-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PUT-006 | Requirement | Putaway & Storage | 2.4 System Rules | docs/scope/02-functional-inbound-storage.md | Stock at dock is visible but *not allocable* until it is put away, unless cross-dock/flow-through is enabled. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-PUT-006-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PUT-007 | Requirement | Putaway & Storage | 2.4 System Rules | docs/scope/02-functional-inbound-storage.md | Putaway tasks are prioritised by: cross-dock urgency > dock congestion (door needed) > dock age > FIFO. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-PUT-007-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PUT-008 | Requirement | Putaway & Storage | 2.4 System Rules | docs/scope/02-functional-inbound-storage.md | Storage zone moves (internal relocation) use the same engine with source ≠ dock. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-PUT-008-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PUT-EX-01 | Exception | Putaway & Storage | 2.7 Exception Handling | docs/scope/02-functional-inbound-storage.md | No location available | Resolution: Route to overflow zone; alert inventory control; capacity report; slotting review flag | M |  |  | TC-PUT-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
PUT-EX-02 | Exception | Putaway & Storage | 2.7 Exception Handling | docs/scope/02-functional-inbound-storage.md | Target location occupied or damaged on arrival | Resolution: Operator reports "location blocked", with location auto-blocked and a count task created; engine re-directs | M |  |  | TC-PUT-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
PUT-EX-03 | Exception | Putaway & Storage | 2.7 Exception Handling | docs/scope/02-functional-inbound-storage.md | LPN over-height / overweight for target | Resolution: Operator reports; LPN dims updated; re-evaluate | M |  |  | TC-PUT-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
PUT-EX-04 | Exception | Putaway & Storage | 2.7 Exception Handling | docs/scope/02-functional-inbound-storage.md | LPN not found at dock | Resolution: Search task; if not found in X min, LPN flagged missing; inventory held; supervisor investigation | M |  |  | TC-PUT-EX-04-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
PUT-EX-05 | Exception | Putaway & Storage | 2.7 Exception Handling | docs/scope/02-functional-inbound-storage.md | Wrong LPN scanned | Resolution: Hard stop; directs to the correct LPN or swaps the task to the scanned LPN if valid | M |  |  | TC-PUT-EX-05-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
PUT-EX-06 | Exception | Putaway & Storage | 2.7 Exception Handling | docs/scope/02-functional-inbound-storage.md | Equipment breakdown mid-task | Resolution: Task suspended with LPN at a drop location (P&D point); re-queued for other equipment | M |  |  | TC-PUT-EX-06-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
OUT-001 | Requirement | Outbound Order Mgmt | 3.5 System Rules | docs/scope/03-functional-outbound.md | Orders with ERP delivery block or credit hold are received but not allocable. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-OUT-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
OUT-002 | Requirement | Outbound Order Mgmt | 3.5 System Rules | docs/scope/03-functional-outbound.md | ERP delivery changes (qty increase/decrease, line add/delete) accepted while status < RELEASED; after release, change requests generate supervisor workflow. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-OUT-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
OUT-003 | Requirement | Outbound Order Mgmt | 3.5 System Rules | docs/scope/03-functional-outbound.md | Cut-off-driven priority: orders not released by release_by_time escalate to priority 1 and raise an alert. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-OUT-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
OUT-004 | Requirement | Outbound Order Mgmt | 3.5 System Rules | docs/scope/03-functional-outbound.md | Ship-complete orders are never partially released unless all lines are allocated (configurable exception: release to pick and hold at pack). | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-OUT-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
OUT-005 | Requirement | Outbound Order Mgmt | 3.5 System Rules | docs/scope/03-functional-outbound.md | Order consolidation: multiple deliveries to the same ship-to, carrier, and ship date may be consolidated into one shipment if the ERP permits (SAP delivery grouping honoured; WMS does not merge ERP deliveries into one ERP document). | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-OUT-005-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
OUT-006 | Requirement | Outbound Order Mgmt | 3.5 System Rules | docs/scope/03-functional-outbound.md | Hazmat orders validated for carrier/service eligibility before release. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-OUT-006-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
OUT-EX-01 | Exception | Outbound Order Mgmt | 3.6 Exception Handling | docs/scope/03-functional-outbound.md | Insufficient inventory | Resolution: Short allocation rule; notify ERP; backorder | M |  |  | TC-OUT-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
OUT-EX-02 | Exception | Outbound Order Mgmt | 3.6 Exception Handling | docs/scope/03-functional-outbound.md | Cancel after release | Resolution: Tasks cancelled if not started; if picked, generate *reverse pick* (return-to-stock) tasks; confirm cancellation to ERP only after stock is back in an allocable status | M |  |  | TC-OUT-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
OUT-EX-03 | Exception | Outbound Order Mgmt | 3.6 Exception Handling | docs/scope/03-functional-outbound.md | Invalid ship-to / carrier | Resolution: Order to ON_HOLD – DATA; integration alert | M |  |  | TC-OUT-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
OUT-EX-04 | Exception | Outbound Order Mgmt | 3.6 Exception Handling | docs/scope/03-functional-outbound.md | Missed cut-off | Resolution: Auto re-plan to next carrier pickup; customer service notified; optional service upgrade rule | M |  |  | TC-OUT-EX-04-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
OUT-EX-05 | Exception | Outbound Order Mgmt | 3.6 Exception Handling | docs/scope/03-functional-outbound.md | Allocated stock becomes unavailable (count variance, damage, QA hold) | Resolution: Automatic re-allocation; if fails → short handling | M |  |  | TC-OUT-EX-05-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
PCK-001 | Requirement | Picking | 4.4 System Rules | docs/scope/03-functional-outbound.md | Every pick requires a location scan (check digit accepted); item scan required unless the location is single-SKU and the item is flagged trust_location (configurable, off for regulated goods). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-PCK-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PCK-002 | Requirement | Picking | 4.4 System Rules | docs/scope/03-functional-outbound.md | Lot/serial scan at pick for items with outbound serial capture; system validates the scanned lot against allocation. A different valid lot is allowed via *lot substitution* if the allocation rule permits it; this triggers re-allocation. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-PCK-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PCK-003 | Requirement | Picking | 4.4 System Rules | docs/scope/03-functional-outbound.md | Short pick triggers: (a) record short with reason, (b) automatic cycle count on location, (c) re-allocation attempt from other locations, (d) if unsuccessful → short-ship handling. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-PCK-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PCK-004 | Requirement | Picking | 4.4 System Rules | docs/scope/03-functional-outbound.md | Pick UoM enforcement: the picker is prompted in the pick UoM (case/each), with conversion displayed; confirming in the wrong UoM is prevented. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-PCK-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PCK-005 | Requirement | Picking | 4.4 System Rules | docs/scope/03-functional-outbound.md | Pick container validation: tote/carton IDs must be unused and of the correct type; LPN is created on first pick. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-PCK-005-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PCK-006 | Requirement | Picking | 4.4 System Rules | docs/scope/03-functional-outbound.md | Task interleaving eligible (§C.3). | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-PCK-006-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PCK-007 | Requirement | Picking | 4.4 System Rules | docs/scope/03-functional-outbound.md | Catch-weight capture at pick for variable-weight items. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-PCK-007-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PCK-008 | Requirement | Picking | 4.4 System Rules | docs/scope/03-functional-outbound.md | Pick-by-line vs. pick-by-order confirmation configurable; partial confirmation allowed. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-PCK-008-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PCK-009 | Requirement | Picking | 4.4 System Rules | docs/scope/03-functional-outbound.md | Picking from locations blocked for counting is prohibited; allocation automatically avoids them. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-PCK-009-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
PCK-EX-01 | Exception | Picking | 4.5 Exception Handling | docs/scope/03-functional-outbound.md | Short pick / location empty | Resolution: PCK-003 flow; location count task with priority | M |  |  | TC-PCK-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
PCK-EX-02 | Exception | Picking | 4.5 Exception Handling | docs/scope/03-functional-outbound.md | Damaged item at location | Resolution: Pick alternate; move damaged unit to DAMAGED status via RF; inventory adjustment workflow | M |  |  | TC-PCK-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
PCK-EX-03 | Exception | Picking | 4.5 Exception Handling | docs/scope/03-functional-outbound.md | Wrong item scanned | Resolution: Hard stop; audible alert; supervisor unlock after 3 consecutive errors | M |  |  | TC-PCK-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
PCK-EX-04 | Exception | Picking | 4.5 Exception Handling | docs/scope/03-functional-outbound.md | Tote full | Resolution: "Tote full" function: close tote, scan new tote, continue (order split across containers) | M |  |  | TC-PCK-EX-04-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
PCK-EX-05 | Exception | Picking | 4.5 Exception Handling | docs/scope/03-functional-outbound.md | Picker abandons task (shift end/break) | Resolution: Task suspended; containers dropped at drop location; task re-assigned with pick progress preserved | M |  |  | TC-PCK-EX-05-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
PCK-EX-06 | Exception | Picking | 4.5 Exception Handling | docs/scope/03-functional-outbound.md | Replenishment not complete when pick arrives | Resolution: Pick task held in WAIT_REPLEN; interleaved; priority boost on the replenishment task | M |  |  | TC-PCK-EX-06-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
PCK-EX-07 | Exception | Picking | 4.5 Exception Handling | docs/scope/03-functional-outbound.md | Expired stock at pick | Resolution: Rejected by validation; stock set to EXPIRED; re-allocate | M |  |  | TC-PCK-EX-07-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
SHP-001 | Requirement | Packing, Staging & Shipping | 5.4 System Rules | docs/scope/03-functional-outbound.md | A carton cannot be closed with unverified items unless supervisor override. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-SHP-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
SHP-002 | Requirement | Packing, Staging & Shipping | 5.4 System Rules | docs/scope/03-functional-outbound.md | Order cannot be loaded unless all cartons are packed and labelled (or partial-ship allowed). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-SHP-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
SHP-003 | Requirement | Packing, Staging & Shipping | 5.4 System Rules | docs/scope/03-functional-outbound.md | Load verification prevents cross-loading (scanned unit's ship-to/route ≠ trailer). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-SHP-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
SHP-004 | Requirement | Packing, Staging & Shipping | 5.4 System Rules | docs/scope/03-functional-outbound.md | Parcel manifest must be closed with the carrier before trailer departure; failure blocks ship confirm for that carrier. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-SHP-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
SHP-005 | Requirement | Packing, Staging & Shipping | 5.4 System Rules | docs/scope/03-functional-outbound.md | Ship confirm is atomic per ERP delivery; if the ERP rejects PGI, the delivery goes to SHIP_ERROR and remains physically shipped. The integration team resolves it within the SLA (§D.6). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-SHP-005-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
SHP-006 | Requirement | Packing, Staging & Shipping | 5.4 System Rules | docs/scope/03-functional-outbound.md | DG shipments require DG documentation, UN labels, and package marks validated before close. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-SHP-006-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
SHP-007 | Requirement | Packing, Staging & Shipping | 5.4 System Rules | docs/scope/03-functional-outbound.md | Serial numbers shipped are reported to ERP per delivery item (SAP serial number profile, Oracle serial transaction). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-SHP-007-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
SHP-EX-01 | Exception | Packing, Staging & Shipping | 5.5 Exception Handling | docs/scope/03-functional-outbound.md | Weight mismatch | Resolution: Audit lane: full re-verify; root cause captured (pick error, master data weight error; master data correction request generated) | M |  |  | TC-SHP-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
SHP-EX-02 | Exception | Packing, Staging & Shipping | 5.5 Exception Handling | docs/scope/03-functional-outbound.md | Carrier label API failure | Resolution: Retry with exponential backoff; fallback to alternate carrier/service if rule permits; otherwise queue and alert | M |  |  | TC-SHP-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
SHP-EX-03 | Exception | Packing, Staging & Shipping | 5.5 Exception Handling | docs/scope/03-functional-outbound.md | Missing carton at loading | Resolution: Trailer cannot close; search task; supervisor may ship short → delivery adjusted (carton re-assigned to next shipment) | M |  |  | TC-SHP-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
SHP-EX-04 | Exception | Packing, Staging & Shipping | 5.5 Exception Handling | docs/scope/03-functional-outbound.md | Trailer capacity exceeded | Resolution: Split load; remaining pallets assigned to new trailer / next pickup | M |  |  | TC-SHP-EX-04-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
SHP-EX-05 | Exception | Packing, Staging & Shipping | 5.5 Exception Handling | docs/scope/03-functional-outbound.md | ERP PGI failure (e.g., period closed, stock inconsistency) | Resolution: Retry; if business error, integration workbench with root cause; must be resolved before ERP period close | M |  |  | TC-SHP-EX-05-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
SHP-EX-06 | Exception | Packing, Staging & Shipping | 5.5 Exception Handling | docs/scope/03-functional-outbound.md | Order cancelled after pack | Resolution: Unpack workflow; items to return-to-stock; labels voided with carrier | M |  |  | TC-SHP-EX-06-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INV-001 | Requirement | Inventory Management | 6.4 System Rules | docs/scope/04-functional-inventory.md | No negative inventory at location level, ever. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INV-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INV-002 | Requirement | Inventory Management | 6.4 System Rules | docs/scope/04-functional-inventory.md | All adjustments require a reason code; each reason code defines the ERP movement mapping, approval requirement, and whether the adjustment counts against inventory accuracy KPIs. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INV-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INV-003 | Requirement | Inventory Management | 6.4 System Rules | docs/scope/04-functional-inventory.md | Count tasks are blind (expected qty not shown). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INV-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INV-004 | Requirement | Inventory Management | 6.4 System Rules | docs/scope/04-functional-inventory.md | Counts in locations with open tasks (pending pick/putaway) are either deferred or computed with open-task awareness ("snapshot at count start" logic). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INV-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INV-005 | Requirement | Inventory Management | 6.4 System Rules | docs/scope/04-functional-inventory.md | Status changes on stock allocated to released orders require de-allocation first; system performs auto re-allocation. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INV-005-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INV-006 | Requirement | Inventory Management | 6.4 System Rules | docs/scope/04-functional-inventory.md | Every inventory transaction captures: user, device, timestamp (UTC), before/after qty, reason, source document, correlation ID for ERP message. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INV-006-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INV-007 | Requirement | Inventory Management | 6.4 System Rules | docs/scope/04-functional-inventory.md | Expiry monitor: nightly job moves expired lots to EXPIRED and generates ERP status change; pre-expiry alerts at configurable days. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INV-007-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INV-008 | Requirement | Inventory Management | 6.4 System Rules | docs/scope/04-functional-inventory.md | Segregation of duties: a user who counted cannot approve their own variance. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INV-008-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
INV-EX-01 | Exception | Inventory Management | 6.5 Exception Handling | docs/scope/04-functional-inventory.md | ERP↔WMS stock variance at reconciliation | Resolution: Reconciliation workbench (§D.6.4): classify (timing, failed message, genuine); re-post or adjust | M |  |  | TC-INV-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INV-EX-02 | Exception | Inventory Management | 6.5 Exception Handling | docs/scope/04-functional-inventory.md | Found stock (no system record) | Resolution: Receive into FOUND status via adjustment; investigate mis-putaway; ERP positive adjustment post-approval | M |  |  | TC-INV-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INV-EX-03 | Exception | Inventory Management | 6.5 Exception Handling | docs/scope/04-functional-inventory.md | Serial mismatch at count | Resolution: Serial exception report; hold serial; investigation | M |  |  | TC-INV-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
INV-EX-04 | Exception | Inventory Management | 6.5 Exception Handling | docs/scope/04-functional-inventory.md | Count exceeds approval threshold | Resolution: Escalation workflow with SLA timer | M |  |  | TC-INV-EX-04-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
RPL-001 | Requirement | Replenishment | 7.3 System Rules | docs/scope/04-functional-inventory.md | Replenishment respects FEFO/FIFO so that the forward location does not receive newer stock while older stock remains in reserve (optional "lot homogeneity" at forward pick). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-RPL-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
RPL-002 | Requirement | Replenishment | 7.3 System Rules | docs/scope/04-functional-inventory.md | Replen priority dynamically increases when dependent pick tasks exist; emergency > wave-driven > min/max > top-off. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-RPL-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
RPL-003 | Requirement | Replenishment | 7.3 System Rules | docs/scope/04-functional-inventory.md | Overflow at forward location: excess returns to reserve or goes to overflow location adjacent. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-RPL-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
RPL-004 | Requirement | Replenishment | 7.3 System Rules | docs/scope/04-functional-inventory.md | Replenishment must complete X minutes before dependent pick release (wave lead-time setting). | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-RPL-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
RPL-005 | Requirement | Replenishment | 7.3 System Rules | docs/scope/04-functional-inventory.md | Min/max parameters recalculated by the slotting engine weekly from velocity (days-of-cover model), subject to approval. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-RPL-005-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
RPL-EX-01 | Exception | Replenishment | 7.4 Exception Handling | docs/scope/04-functional-inventory.md | No reserve stock | Resolution: Short in forward → pick shorts → backorder; purchase signal report to ERP planner | M |  |  | TC-RPL-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
RPL-EX-02 | Exception | Replenishment | 7.4 Exception Handling | docs/scope/04-functional-inventory.md | Reserve LPN short | Resolution: Count task on reserve; re-source | M |  |  | TC-RPL-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
RPL-EX-03 | Exception | Replenishment | 7.4 Exception Handling | docs/scope/04-functional-inventory.md | Forward location full / mis-slotted item present | Resolution: Location exception; count; relocation task | M |  |  | TC-RPL-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
RET-001 | Requirement | Returns | 8.4 System Rules | docs/scope/04-functional-inventory.md | Serial returned must match a serial previously shipped to that customer; mismatches flag potential fraud. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-RET-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
RET-002 | Requirement | Returns | 8.4 System Rules | docs/scope/04-functional-inventory.md | Returned quantity > RMA quantity requires override. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-RET-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
RET-003 | Requirement | Returns | 8.4 System Rules | docs/scope/04-functional-inventory.md | Regulated products (pharma, food) default to non-saleable unless QA release. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-RET-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
RET-004 | Requirement | Returns | 8.4 System Rules | docs/scope/04-functional-inventory.md | Condition, reason, and disposition captured per unit and sent to ERP for credit decision. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-RET-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
RET-005 | Requirement | Returns | 8.4 System Rules | docs/scope/04-functional-inventory.md | Photos attachable per unit (mandatory for grade C/D above value threshold). | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-RET-005-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
RET-006 | Requirement | Returns | 8.4 System Rules | docs/scope/04-functional-inventory.md | RTV consolidation per vendor with RTV authorisation number required before shipment. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-RET-006-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
RET-EX-01 | Exception | Returns | 8.5 Exception Handling | docs/scope/04-functional-inventory.md | No RMA / unidentifiable | Resolution: Hold in returns problem-solve location with photo; customer service case | M |  |  | TC-RET-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
RET-EX-02 | Exception | Returns | 8.5 Exception Handling | docs/scope/04-functional-inventory.md | Wrong item returned | Resolution: Receive as actual item with flag; ERP notified for credit adjustment | M |  |  | TC-RET-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
RET-EX-03 | Exception | Returns | 8.5 Exception Handling | docs/scope/04-functional-inventory.md | Serial not shipped by us | Resolution: Quarantine; fraud workflow | M |  |  | TC-RET-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
RET-EX-04 | Exception | Returns | 8.5 Exception Handling | docs/scope/04-functional-inventory.md | RTV refused by vendor | Resolution: Re-disposition (scrap / liquidate) | M |  |  | TC-RET-EX-04-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
XDK-001 | Requirement | Cross-Docking | 9.3 System Rules | docs/scope/04-functional-inventory.md | Cross-dock priority: backorders of priority customers > planned cross-dock > regular orders due today. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-XDK-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
XDK-002 | Requirement | Cross-Docking | 9.3 System Rules | docs/scope/04-functional-inventory.md | Cross-dock only for stock received as AVAILABLE (QI stock never cross-docked). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-XDK-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
XDK-003 | Requirement | Cross-Docking | 9.3 System Rules | docs/scope/04-functional-inventory.md | Lot/expiry constraints of the outbound customer still apply. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-XDK-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
XDK-004 | Requirement | Cross-Docking | 9.3 System Rules | docs/scope/04-functional-inventory.md | Dwell time SLA (e.g., ≤ 24 h in staging) with alerting. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-XDK-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
XDK-EX-01 | Exception | Cross-Docking | 9.4 Exception Handling | docs/scope/04-functional-inventory.md | Inbound short vs planned cross-dock allocation | Resolution: Fair-share or priority allocation across destinations; shortfall to regular fulfilment | M |  |  | TC-XDK-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
XDK-EX-02 | Exception | Cross-Docking | 9.4 Exception Handling | docs/scope/04-functional-inventory.md | Outbound trailer not available | Resolution: Staged stock remains allocated; after dwell SLA → putaway with allocation kept | M |  |  | TC-XDK-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
XDK-EX-03 | Exception | Cross-Docking | 9.4 Exception Handling | docs/scope/04-functional-inventory.md | Outbound order cancelled after cross-dock split | Resolution: Redirect to putaway | M |  |  | TC-XDK-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
VAS-001 | Requirement | Value-Added Services | 10.3 System Rules | docs/scope/05-functional-specialised.md | VAS work orders are sequenced to complete before the order's pack deadline; VAS lead time is included in the release-by calculation. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-VAS-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
VAS-002 | Requirement | Value-Added Services | 10.3 System Rules | docs/scope/05-functional-specialised.md | VAS station capacity (operators × standard minutes) is a constraint in wave planning. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-VAS-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
VAS-003 | Requirement | Value-Added Services | 10.3 System Rules | docs/scope/05-functional-specialised.md | Each VAS completion generates a billable event (3PL) with quantity, service code, and owner. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-VAS-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
VAS-004 | Requirement | Value-Added Services | 10.3 System Rules | docs/scope/05-functional-specialised.md | Label print jobs are data-driven templates (ZPL/label designer) versioned per customer. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-VAS-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
VAS-EX-01 | Exception | Value-Added Services | 10.4 Exceptions | docs/scope/05-functional-specialised.md | Consumable out of stock | Resolution: Replenish consumable; order held at VAS with alert | M |  |  | TC-VAS-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
VAS-EX-02 | Exception | Value-Added Services | 10.4 Exceptions | docs/scope/05-functional-specialised.md | Unit damaged during VAS | Resolution: Damage adjustment; re-pick replacement | M |  |  | TC-VAS-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
VAS-EX-03 | Exception | Value-Added Services | 10.4 Exceptions | docs/scope/05-functional-specialised.md | Instruction missing / ambiguous | Resolution: Hold with "instruction required"; customer service/3PL account manager task | M |  |  | TC-VAS-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
KIT-001 | Requirement | Kitting / Light Mfg | 11.3 System Rules | docs/scope/05-functional-specialised.md | BOM version effective at the work-order date is used; BOM master is received from ERP (SAP BOMMAT / CS BOM; Oracle BOM_STRUCTURES_B). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-KIT-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
KIT-002 | Requirement | Kitting / Light Mfg | 11.3 System Rules | docs/scope/05-functional-specialised.md | Component lot/serial genealogy is recorded against the parent serial/lot. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-KIT-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
KIT-003 | Requirement | Kitting / Light Mfg | 11.3 System Rules | docs/scope/05-functional-specialised.md | Kit cannot be completed with missing components unless an approved substitute component is defined. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-KIT-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
KIT-004 | Requirement | Kitting / Light Mfg | 11.3 System Rules | docs/scope/05-functional-specialised.md | Partial completion allowed; remaining components stay allocated to the work order. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-KIT-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
KIT-005 | Requirement | Kitting / Light Mfg | 11.3 System Rules | docs/scope/05-functional-specialised.md | Parent lot expiry = min(component expiry) unless rule overrides. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-KIT-005-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
KIT-EX-01 | Exception | Kitting / Light Mfg | 11.4 Exceptions | docs/scope/05-functional-specialised.md | Component short | Resolution: Hold WO; partial build; substitution workflow | M |  |  | TC-KIT-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
KIT-EX-02 | Exception | Kitting / Light Mfg | 11.4 Exceptions | docs/scope/05-functional-specialised.md | Component defective during assembly | Resolution: Scrap component with reason; re-pick | M |  |  | TC-KIT-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
KIT-EX-03 | Exception | Kitting / Light Mfg | 11.4 Exceptions | docs/scope/05-functional-specialised.md | ERP order closed / technically completed during build | Resolution: Posting rejected → integration workbench; supervisor decides | M |  |  | TC-KIT-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
QM-001 | Requirement | Quality Management | 12.6 System Rules | docs/scope/05-functional-specialised.md | QI/blocked stock is never allocable; never pickable except for sample pull, RTV, or scrap tasks. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-QM-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
QM-002 | Requirement | Quality Management | 12.6 System Rules | docs/scope/05-functional-specialised.md | QA release requires e-signature for regulated item classes. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-QM-002-01 | Functional (rule test harness + E2E scenario); Regulated validation (OQ) | SIT; UAT | Not Started
QM-003 | Requirement | Quality Management | 12.6 System Rules | docs/scope/05-functional-specialised.md | Sample quantities consumed are posted to ERP as sample consumption (SAP mvt 333 / 331; Oracle misc issue with alias). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-QM-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
QM-004 | Requirement | Quality Management | 12.6 System Rules | docs/scope/05-functional-specialised.md | Hold placed by ERP (batch status restricted) must be reflected in WMS within 60 seconds. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-QM-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
QM-005 | Requirement | Quality Management | 12.6 System Rules | docs/scope/05-functional-specialised.md | Recall trace across genealogy (kits, repacks) must return complete results. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-QM-005-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
QM-EX-01 | Exception | Quality Management | 12.7 Exceptions | docs/scope/05-functional-specialised.md | UD received for stock already moved/consumed | Resolution: Apply to remaining qty; discrepancy report | M |  |  | TC-QM-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
QM-EX-02 | Exception | Quality Management | 12.7 Exceptions | docs/scope/05-functional-specialised.md | Sample pull short | Resolution: Adjust sample plan; inspector notified | M |  |  | TC-QM-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
QM-EX-03 | Exception | Quality Management | 12.7 Exceptions | docs/scope/05-functional-specialised.md | Recall of lot partially in transit | Resolution: Carrier intercept request; flag shipments | M |  |  | TC-QM-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
MWH-001 | Requirement | Multi-WH & 3PL | 13.3 System Rules | docs/scope/05-functional-specialised.md | Cross-owner data access is impossible for owner-scoped users (enforced at data layer, not UI only). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-MWH-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
MWH-002 | Requirement | Multi-WH & 3PL | 13.3 System Rules | docs/scope/05-functional-specialised.md | Mixed-owner LPN or location forbidden unless shared storage enabled; even then, inventory record carries single owner. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-MWH-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
MWH-003 | Requirement | Multi-WH & 3PL | 13.3 System Rules | docs/scope/05-functional-specialised.md | Billing events are immutable; corrections are credit/debit adjustment events. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-MWH-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
MWH-004 | Requirement | Multi-WH & 3PL | 13.3 System Rules | docs/scope/05-functional-specialised.md | Inter-site in-transit visible in both sites and reconciled against ERP in-transit stock. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-MWH-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
MWH-005 | Requirement | Multi-WH & 3PL | 13.3 System Rules | docs/scope/05-functional-specialised.md | Onboarding of a new client is achievable via configuration only (no code), within 10 business days for a standard profile. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-MWH-005-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
MWH-EX-01 | Exception | Multi-WH & 3PL | 13.4 Exceptions | docs/scope/05-functional-specialised.md | Inter-site shipment received short | Resolution: Discrepancy recorded at receiving site; ERP in-transit difference; claim workflow | M |  |  | TC-MWH-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
MWH-EX-02 | Exception | Multi-WH & 3PL | 13.4 Exceptions | docs/scope/05-functional-specialised.md | Billing rate missing for event | Resolution: Event held in UNRATED; account manager alert; invoice blocked until resolved | M |  |  | TC-MWH-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
MWH-EX-03 | Exception | Multi-WH & 3PL | 13.4 Exceptions | docs/scope/05-functional-specialised.md | Client master item conflict | Resolution: Integration reject with explicit owner + item key error | M |  |  | TC-MWH-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
CCH-001 | Requirement | Cold Chain & HazMat | 14.3 System Rules | docs/scope/05-functional-specialised.md | Temperature class compatibility checks are hard constraints across putaway, replenishment, staging, and loading. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-CCH-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
CCH-002 | Requirement | Cold Chain & HazMat | 14.3 System Rules | docs/scope/05-functional-specialised.md | TOR limit breach places LPN on automatic hold. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-CCH-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
CCH-003 | Requirement | Cold Chain & HazMat | 14.3 System Rules | docs/scope/05-functional-specialised.md | DG segregation matrix enforced at putaway and trailer load. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-CCH-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
CCH-004 | Requirement | Cold Chain & HazMat | 14.3 System Rules | docs/scope/05-functional-specialised.md | Compartment quantity limits enforced (aggregate kg/L per class per compartment). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-CCH-004-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
CCH-005 | Requirement | Cold Chain & HazMat | 14.3 System Rules | docs/scope/05-functional-specialised.md | DG tasks only assignable to certified users. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-CCH-005-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
CCH-006 | Requirement | Cold Chain & HazMat | 14.3 System Rules | docs/scope/05-functional-specialised.md | Excursion data (sensor series) retained for product shelf life + 1 year minimum. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-CCH-006-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
CCH-EX-01 | Exception | Cold Chain & HazMat | 14.4 Exceptions | docs/scope/05-functional-specialised.md | Room temperature excursion | Resolution: Auto-hold all LPNs in area during excursion window; QA workflow; facilities alert | M |  |  | TC-CCH-EX-01-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
CCH-EX-02 | Exception | Cold Chain & HazMat | 14.4 Exceptions | docs/scope/05-functional-specialised.md | Sensor offline | Resolution: Alert; manual reading task every N minutes until restored; data gap documented | M |  |  | TC-CCH-EX-02-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
CCH-EX-03 | Exception | Cold Chain & HazMat | 14.4 Exceptions | docs/scope/05-functional-specialised.md | DG compartment limit reached | Resolution: Putaway redirected; if none, receipt hold | M |  |  | TC-CCH-EX-03-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
CCH-EX-04 | Exception | Cold Chain & HazMat | 14.4 Exceptions | docs/scope/05-functional-specialised.md | Carrier rejects DG | Resolution: Re-route per DG service rules | M |  |  | TC-CCH-EX-04-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
CCH-EX-05 | Exception | Cold Chain & HazMat | 14.4 Exceptions | docs/scope/05-functional-specialised.md | Uncertified user attempts DG task | Resolution: Task blocked; supervisor notified | M |  |  | TC-CCH-EX-05-01 | Negative / exception scenario | SIT; UAT | Not Started |  |  | Priority defaulted to M (exception flow; see Legend)
ADV-001 | Requirement | Advanced Features | C.1 Slotting & Optimisation Engine | docs/scope/06-advanced-features.md | Weekly automated slotting recommendations with approval workflow | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-001-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-002 | Requirement | Advanced Features | C.1 Slotting & Optimisation Engine | docs/scope/06-advanced-features.md | Constraint-aware (hard constraints never violated) | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-ADV-002-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-003 | Requirement | Advanced Features | C.1 Slotting & Optimisation Engine | docs/scope/06-advanced-features.md | Move plan executable as system tasks with before/after KPI tracking | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-003-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-010 | Requirement | Advanced Features | C.2 Labor Management System (LMS) | docs/scope/06-advanced-features.md | Discrete engineered standards for all RF task types | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-010-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-011 | Requirement | Advanced Features | C.2 Labor Management System (LMS) | docs/scope/06-advanced-features.md | Real-time operator performance dashboard | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-011-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-012 | Requirement | Advanced Features | C.2 Labor Management System (LMS) | docs/scope/06-advanced-features.md | Labor planning by shift/hour from backlog and forecast | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-012-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-013 | Requirement | Advanced Features | C.2 Labor Management System (LMS) | docs/scope/06-advanced-features.md | Works council / privacy configuration: aggregation-only mode where individual tracking is legally restricted (e.g., DE, FR) | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-ADV-013-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-020 | Requirement | Advanced Features | C.3 Task Interleaving Algorithms | docs/scope/06-advanced-features.md | Configurable interleaving by equipment class and zone | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-020-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-021 | Requirement | Advanced Features | C.3 Task Interleaving Algorithms | docs/scope/06-advanced-features.md | Task selection latency ≤ 300 ms p95 with ≥ 50,000 open tasks | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-ADV-021-01 | Performance | PERF | Not Started
ADV-030 | Requirement | Advanced Features | C.4 Wave Planning Engine | docs/scope/06-advanced-features.md | Wave templates with simulation ("plan wave" preview without release) | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-ADV-030-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-031 | Requirement | Advanced Features | C.4 Wave Planning Engine | docs/scope/06-advanced-features.md | Waveless release with WIP-based throttling | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-031-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-032 | Requirement | Advanced Features | C.4 Wave Planning Engine | docs/scope/06-advanced-features.md | Wave release of 10,000 orders / 50,000 lines completes ≤ 60 s | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-ADV-032-01 | Performance | PERF | Not Started
ADV-040 | Requirement | Advanced Features | C.5 Cartonization Engine | docs/scope/06-advanced-features.md | Cartonization at release with pick-to-carton support | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-040-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-041 | Requirement | Advanced Features | C.5 Cartonization Engine | docs/scope/06-advanced-features.md | Carton recommendation ≤ 50 ms p95 per multi-item order | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-041-01 | Performance | PERF | Not Started
ADV-042 | Requirement | Advanced Features | C.5 Cartonization Engine | docs/scope/06-advanced-features.md | Carton catalogue per site/owner with cost and dim-weight divisors per carrier | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-042-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-050 | Requirement | Advanced Features | C.6 Automation & Robotics Integration (AMR / AGV / ASRS) | docs/scope/06-advanced-features.md | Vendor-neutral automation adaptor framework; new vendor adaptor ≤ 8 weeks | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-050-01 | Automation / MHE (emulator, FAT/SAT) | SIT; Site | Not Started
ADV-051 | Requirement | Advanced Features | C.6 Automation & Robotics Integration (AMR / AGV / ASRS) | docs/scope/06-advanced-features.md | VDA 5050 v2 support for AGV/AMR | Rule/requirement enforced as stated (positive + negative case) | C |  |  | TC-ADV-051-01 | Automation / MHE (emulator, FAT/SAT) | SIT; Site | Not Started
ADV-052 | Requirement | Advanced Features | C.6 Automation & Robotics Integration (AMR / AGV / ASRS) | docs/scope/06-advanced-features.md | Sorter routing response ≤ 100 ms p99 | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-ADV-052-01 | Performance | PERF | Not Started |  |  | Priority qualifier: if sorter in scope
ADV-053 | Requirement | Advanced Features | C.6 Automation & Robotics Integration (AMR / AGV / ASRS) | docs/scope/06-advanced-features.md | Automation inventory reconciliation with discrepancy workflow | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-ADV-053-01 | Automation / MHE (emulator, FAT/SAT) | SIT; Site | Not Started
ADV-060 | Requirement | Advanced Features | C.7 IoT Sensor Integration | docs/scope/06-advanced-features.md | Ingest ≥ 5,000 sensor readings/s per tenant | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-060-01 | Performance | PERF | Not Started
ADV-061 | Requirement | Advanced Features | C.7 IoT Sensor Integration | docs/scope/06-advanced-features.md | Rule evaluation to WMS event latency ≤ 10 s | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-061-01 | Performance | PERF | Not Started
ADV-062 | Requirement | Advanced Features | C.7 IoT Sensor Integration | docs/scope/06-advanced-features.md | Device identity and certificate rotation | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-ADV-062-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-070 | Requirement | Advanced Features | C.8 AI-Driven Forecasting & Predictive Analytics | docs/scope/06-advanced-features.md | Hourly outbound volume forecast with WAPE ≤ 15% at site-day level (after 12 weeks of history) | Rule/requirement enforced as stated (positive + negative case) | C |  |  | TC-ADV-070-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-071 | Requirement | Advanced Features | C.8 AI-Driven Forecasting & Predictive Analytics | docs/scope/06-advanced-features.md | Late-order risk scoring feeding exception dashboard | Rule/requirement enforced as stated (positive + negative case) | C |  |  | TC-ADV-071-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-072 | Requirement | Advanced Features | C.8 AI-Driven Forecasting & Predictive Analytics | docs/scope/06-advanced-features.md | Explainability: top feature contributions displayed for each recommendation | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-ADV-072-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-080 | Requirement | Advanced Features | C.9 Digital Twin for Warehouse Simulation | docs/scope/06-advanced-features.md | Simulation uses production rule engines (no separate re-implementation) | Rule/requirement enforced as stated (positive + negative case) | C |  |  | TC-ADV-080-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-081 | Requirement | Advanced Features | C.9 Digital Twin for Warehouse Simulation | docs/scope/06-advanced-features.md | 8-hour shift simulation for a 50k-line day runs ≤ 5 min | Rule/requirement enforced as stated (positive + negative case) | C |  |  | TC-ADV-081-01 | Performance | PERF | Not Started
ADV-090 | Requirement | Advanced Features | C.10 Computer Vision for Inventory & Safety Monitoring | docs/scope/06-advanced-features.md | CV count observations integrated into cycle-count workflow | Rule/requirement enforced as stated (positive + negative case) | C |  |  | TC-ADV-090-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-091 | Requirement | Advanced Features | C.10 Computer Vision for Inventory & Safety Monitoring | docs/scope/06-advanced-features.md | Dock damage evidence attached to receipt exceptions | Rule/requirement enforced as stated (positive + negative case) | C |  |  | TC-ADV-091-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started
ADV-092 | Requirement | Advanced Features | C.10 Computer Vision for Inventory & Safety Monitoring | docs/scope/06-advanced-features.md | Edge anonymisation of persons by default | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-ADV-092-01 | Functional (rule test harness + E2E scenario) | SIT; UAT | Not Started |  |  | Priority qualifier: if CV in scope
INT-001 | Requirement | ERP Integration | D.2 Master Data Flows (ERP → WMS) | docs/scope/07-erp-integration.md | Master data messages are idempotent upserts keyed by ERP key plus owner (3PL). Deletions are soft (flag ERP_DELETED), and objects that are still referenced by open inventory or orders are never physically deleted. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INT-001-01 | Integration (component) + end-to-end SIT | SIT | Not Started
INT-002 | Requirement | ERP Integration | D.2 Master Data Flows (ERP → WMS) | docs/scope/07-erp-integration.md | Transactions that reference an unknown master are *parked*, not rejected. They are automatically retried when the master arrives, with a timeout alert after 30 min. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INT-002-01 | Integration (component) + end-to-end SIT | SIT | Not Started
INT-003 | Requirement | ERP Integration | D.2 Master Data Flows (ERP → WMS) | docs/scope/07-erp-integration.md | WMS-measured dimensions and weights can be sent back to the ERP (SAP BAPI_MATERIAL_SAVEDATA / API_PRODUCT_SRV PATCH; Oracle item update) under a data-governance approval flag. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-INT-003-01 | Integration (component) + end-to-end SIT | SIT | Not Started
INT-010 | Requirement | ERP Integration | D.6.2 Error Handling Rules | docs/scope/07-erp-integration.md | Physical warehouse operation must never be blocked by an ERP outage or error; confirmations queue and post when resolved (store-and-forward). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INT-010-01 | Integration (component) + end-to-end SIT | SIT | Not Started
INT-011 | Requirement | ERP Integration | D.6.2 Error Handling Rules | docs/scope/07-erp-integration.md | Every WMS→ERP confirmation must have a terminal state: POSTED (with ERP doc no.), REJECTED_RESOLVED, or CANCELLED_WITH_APPROVAL. None may remain in error beyond SLA (default 24 h; before period close: 4 h). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INT-011-01 | Integration (component) + end-to-end SIT | SIT | Not Started
INT-012 | Requirement | ERP Integration | D.6.2 Error Handling Rules | docs/scope/07-erp-integration.md | Application acknowledgements are mandatory: technical ACK ≠ business success. SAP confirmations capture returned material document numbers; ALEAUD for IDoc status 53/51. Oracle interface rows are polled for PROCESS_FLAG/ERROR_CODE and MTL_TRANSACTIONS_INTERFACE.ERROR_EXPLANATION. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INT-012-01 | Integration (component) + end-to-end SIT | SIT | Not Started
INT-013 | Requirement | ERP Integration | D.6.2 Error Handling Rules | docs/scope/07-erp-integration.md | Sequencing: a later confirmation for the same document is held until the earlier one is posted (prevents out-of-order PGI before split, etc.). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INT-013-01 | Integration (component) + end-to-end SIT | SIT | Not Started
INT-014 | Requirement | ERP Integration | D.6.2 Error Handling Rules | docs/scope/07-erp-integration.md | Reprocessing is idempotent; ERP-side duplicate check uses WMS confirmation ID stored in ERP reference field (SAP XBLNR/BKTXT/delivery extension; Oracle ATTRIBUTE/source line ref). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INT-014-01 | Integration (component) + end-to-end SIT | SIT | Not Started
INT-015 | Requirement | ERP Integration | D.6.2 Error Handling Rules | docs/scope/07-erp-integration.md | Period-end cut-off: a configurable freeze window blocks WMS postings dated in the old period after close; confirmations are posted in the new period with the original physical date captured in reference. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-INT-015-01 | Integration (component) + end-to-end SIT | SIT | Not Started
IF-IB-001 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Inbound delivery / ASN (ERP→WMS), trigger: Create/change | SAP: DELVRY07 SHP_IBDLV_SAVE_REPLICA ¦ Oracle: ASN extract / REST ¦ Design peak: 5k/day ¦ Latency SLA: ≤ 2 min | M |  |  | TC-IF-IB-001-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-IB-002 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Receipt confirmation (WMS→ERP), trigger: Receipt close / LPN | SAP: BAPI_INB_DELIVERY_CONFIRM_DEC ¦ Oracle: RCV interface / receivingReceiptRequests ¦ Design peak: 5k/day ¦ Latency SLA: ≤ 2 min | M |  |  | TC-IF-IB-002-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-INV-001 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Goods movements (adjust, status, scrap, transfer) (WMS→ERP), trigger: Event | SAP: BAPI_GOODSMVT_CREATE / MBGMCR ¦ Oracle: MTL_TRANSACTIONS_INTERFACE / inventoryStagedTransactions ¦ Design peak: 30k/day ¦ Latency SLA: ≤ 2 min | M |  |  | TC-IF-INV-001-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-INV-002 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | ERP-originated status changes (QM UD, batch restriction) (ERP→WMS), trigger: Event | SAP: Event Mesh / custom IDoc ¦ Oracle: Business event / polling ¦ Design peak: 2k/day ¦ Latency SLA: ≤ 60 s | M |  |  | TC-IF-INV-002-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-INV-003 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Stock reconciliation snapshot (Bidirectional), trigger: Scheduled (daily + on-demand) | SAP: API_MATERIAL_STOCK_SRV / RFC extract ¦ Oracle: Onhand extract (BIP / REST) ¦ Design peak: Full snapshot ¦ Latency SLA: ≤ 30 min | M |  |  | TC-IF-INV-003-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-INV-004 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Physical inventory (WMS→ERP), trigger: Count approval | SAP: BAPI_MATERIAL_PHYSINV_* ¦ Oracle: MTL_CC_ENTRIES_INTERFACE ¦ Design peak: 10k/day ¦ Latency SLA: ≤ 5 min | M |  |  | TC-IF-INV-004-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-KIT-001 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Kit consumption/production (WMS→ERP), trigger: Completion | SAP: GM 261/101 / confirmation ¦ Oracle: WIP interfaces / work order txns ¦ Design peak: 5k/day ¦ Latency SLA: ≤ 5 min | M |  |  | TC-IF-KIT-001-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-MD-001 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Item (ERP→WMS), trigger: Change | SAP: MATMAS / OData ¦ Oracle: Event + REST / extract ¦ Design peak: 50k/day ¦ Latency SLA: ≤ 5 min | M |  |  | TC-IF-MD-001-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-MD-002 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Customer/Ship-to (ERP→WMS), trigger: Change | SAP: DEBMAS / BP API ¦ Oracle: TCA extract / REST ¦ Design peak: 10k/day ¦ Latency SLA: ≤ 15 min | M |  |  | TC-IF-MD-002-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-MD-003 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Vendor (ERP→WMS), trigger: Change | SAP: CREMAS / BP API ¦ Oracle: Supplier REST ¦ Design peak: 2k/day ¦ Latency SLA: ≤ 15 min | M |  |  | TC-IF-MD-003-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-MD-004 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Batch / status (ERP→WMS), trigger: Change | SAP: BATMAS+CLFMAS ¦ Oracle: Lot / status ¦ Design peak: 20k/day ¦ Latency SLA: ≤ 60 s (status) | M |  |  | TC-IF-MD-004-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-OB-001 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Outbound delivery / shipment request (ERP→WMS), trigger: Create/change | SAP: DELVRY07 SHP_OBDLV_SAVE_REPLICA ¦ Oracle: Shipment Request ¦ Design peak: 200k/day ¦ Latency SLA: ≤ 1 min | M |  |  | TC-IF-OB-001-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-OB-002 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Cancel / change response (WMS→ERP), trigger: On request | SAP: ALEAUD / status ¦ Oracle: Shipment Request ack ¦ Design peak: 5k/day ¦ Latency SLA: ≤ 1 min | M |  |  | TC-IF-OB-002-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-OB-003 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Shipment confirmation + PGI (WMS→ERP), trigger: Trailer close / parcel ship | SAP: BAPI_OUTB_DELIVERY_CONFIRM_DEC ¦ Oracle: Shipment Advice / ship confirm ¦ Design peak: 200k/day ¦ Latency SLA: ≤ 2 min | M |  |  | TC-IF-OB-003-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-OB-004 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Delivery split (WMS→ERP), trigger: Short | SAP: BAPI_OUTB_DELIVERY_SPLIT_DEC ¦ Oracle: (via Shipment Advice backorder) ¦ Design peak: 5k/day ¦ Latency SLA: ≤ 2 min | M |  |  | TC-IF-OB-004-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-RET-001 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Returns expectation (ERP→WMS), trigger: Create | SAP: DELVRY07 (LR) ¦ Oracle: RMA ¦ Design peak: 10k/day ¦ Latency SLA: ≤ 5 min | M |  |  | TC-IF-RET-001-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
IF-RET-002 | Interface | ERP Interfaces | D.4.2 Interface Catalogue (Summary) | docs/scope/07-erp-integration.md | Returns receipt + disposition (WMS→ERP), trigger: Receipt | SAP: BAPI_INB_DELIVERY_CONFIRM_DEC + GM ¦ Oracle: RCV interface + transfers ¦ Design peak: 10k/day ¦ Latency SLA: ≤ 5 min | M |  |  | TC-IF-RET-002-01 | Interface test per ISD (positive, negative, idempotency, ordering) | SIT | Not Started |  |  | Priority defaulted to M (interface in catalogue D.4.2)
NFR-001 | Requirement | Non-Functional | E.1 Scalability | docs/scope/08-non-functional-requirements.md | Horizontal scaling of stateless services (API, task, allocation, integration) via container orchestration autoscaling on CPU, queue depth, and p95 latency. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-001-01 | Performance / scalability | PERF | Not Started
NFR-002 | Requirement | Non-Functional | E.1 Scalability | docs/scope/08-non-functional-requirements.md | Data partitioned by tenant_id + site_id; large tenants can be placed on dedicated database clusters (cell-based architecture) without code change. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-002-01 | Performance / scalability | PERF | Not Started
NFR-003 | Requirement | Non-Functional | E.1 Scalability | docs/scope/08-non-functional-requirements.md | Adding a site requires no downtime and no schema change. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-003-01 | Performance / scalability | PERF | Not Started
NFR-004 | Requirement | Non-Functional | E.1 Scalability | docs/scope/08-non-functional-requirements.md | Linear throughput scaling to 3× reference load demonstrated in performance test with ≤ 10% p95 degradation. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-004-01 | Performance / scalability | PERF | Not Started
NFR-005 | Requirement | Non-Functional | E.1 Scalability | docs/scope/08-non-functional-requirements.md | Peak handling: 4× average hourly volume sustained for 4 h (e.g., Black Friday), pre-scaling via scheduled capacity profiles. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-005-01 | Performance / scalability | PERF | Not Started
NFR-020 | Requirement | Non-Functional | E.3 High Availability & Disaster Recovery | docs/scope/08-non-functional-requirements.md | Service availability (monthly, excluding agreed maintenance) | Target: 99.95% (≤ 22 min/month) | M |  |  | TC-NFR-020-01 | Resilience / DR | PERF; DR | Not Started |  |  | Priority defaulted to M (HA/DR target; see Legend)
NFR-021 | Requirement | Non-Functional | E.3 High Availability & Disaster Recovery | docs/scope/08-non-functional-requirements.md | Planned maintenance | Target: Zero-downtime deployments (rolling / blue-green); schema migrations backward-compatible (expand/contract) | M |  |  | TC-NFR-021-01 | Resilience / DR | PERF; DR | Not Started |  |  | Priority defaulted to M (HA/DR target; see Legend)
NFR-022 | Requirement | Non-Functional | E.3 High Availability & Disaster Recovery | docs/scope/08-non-functional-requirements.md | Multi-AZ deployment of all tiers | Target: 3 availability zones; synchronous DB replication within region | M |  |  | TC-NFR-022-01 | Resilience / DR | PERF; DR | Not Started |  |  | Priority defaulted to M (HA/DR target; see Legend)
NFR-023 | Requirement | Non-Functional | E.3 High Availability & Disaster Recovery | docs/scope/08-non-functional-requirements.md | RPO (regional disaster) | Target: ≤ 5 min (asynchronous cross-region replication) | M |  |  | TC-NFR-023-01 | Resilience / DR | PERF; DR | Not Started |  |  | Priority defaulted to M (HA/DR target; see Legend)
NFR-024 | Requirement | Non-Functional | E.3 High Availability & Disaster Recovery | docs/scope/08-non-functional-requirements.md | RTO (regional disaster) | Target: ≤ 1 h (warm standby region; runbook-automated failover) | M |  |  | TC-NFR-024-01 | Resilience / DR | PERF; DR | Not Started |  |  | Priority defaulted to M (HA/DR target; see Legend)
NFR-025 | Requirement | Non-Functional | E.3 High Availability & Disaster Recovery | docs/scope/08-non-functional-requirements.md | DR testing | Target: Full failover test at least twice per year with evidence report | M |  |  | TC-NFR-025-01 | Resilience / DR | PERF; DR | Not Started |  |  | Priority defaulted to M (HA/DR target; see Legend)
NFR-026 | Requirement | Non-Functional | E.3 High Availability & Disaster Recovery | docs/scope/08-non-functional-requirements.md | Backups | Target: Continuous PITR (35 days); daily snapshot copied cross-region; monthly immutable backup retained 12 months (WORM) | M |  |  | TC-NFR-026-01 | Resilience / DR | PERF; DR | Not Started |  |  | Priority defaulted to M (HA/DR target; see Legend)
NFR-027 | Requirement | Non-Functional | E.3 High Availability & Disaster Recovery | docs/scope/08-non-functional-requirements.md | Site resilience (edge) | Target: Optional *site edge node* for automation-heavy sites: local continuation of sorter routing & automation orchestration for ≥ 4 h of WAN loss, sync on reconnect | M |  |  | TC-NFR-027-01 | Resilience / DR | PERF; DR | Not Started |  |  | Priority defaulted to M (HA/DR target; see Legend)
NFR-028 | Requirement | Non-Functional | E.3 High Availability & Disaster Recovery | docs/scope/08-non-functional-requirements.md | RF device offline mode | Target: Limited offline continuation for putaway/pick confirmations for ≤ 15 min with queued sync & conflict detection | M |  |  | TC-NFR-028-01 | Resilience / DR | PERF; DR | Not Started |  |  | Priority defaulted to M (HA/DR target; see Legend)
NFR-029 | Requirement | Non-Functional | E.3 High Availability & Disaster Recovery | docs/scope/08-non-functional-requirements.md | ERP outage | Target: Warehouse continues operating indefinitely on already-received orders; confirmations queued (INT-010) | M |  |  | TC-NFR-029-01 | Resilience / DR | PERF; DR | Not Started |  |  | Priority defaulted to M (HA/DR target; see Legend)
NFR-030 | Requirement | Non-Functional | E.3 High Availability & Disaster Recovery | docs/scope/08-non-functional-requirements.md | Degraded modes | Target: Documented playbooks: carrier API down (pre-printed label pools / later manifest), print server down (alternate printer routing), WCS down (manual task conversion) | M |  |  | TC-NFR-030-01 | Resilience / DR | PERF; DR | Not Started |  |  | Priority defaulted to M (HA/DR target; see Legend)
NFR-040 | Requirement | Non-Functional | E.5 Configurability & Extensibility | docs/scope/08-non-functional-requirements.md | Business rules (allocation, putaway, replenishment, wave templates, cartonization constraints, disposition, tolerances) are configured through UI/rule tables, not code. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-040-01 | Configuration verification | SIT | Not Started
NFR-041 | Requirement | Non-Functional | E.5 Configurability & Extensibility | docs/scope/08-non-functional-requirements.md | Configuration is versioned, promotable between environments (export/import as signed packages), and diff-able; effective-dated changes. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-041-01 | Configuration verification | SIT | Not Started
NFR-042 | Requirement | Non-Functional | E.5 Configurability & Extensibility | docs/scope/08-non-functional-requirements.md | Custom attributes (user-defined fields) on item, LPN, inventory, order, order line, location, with validation and UI/reporting exposure, without schema change by the customer. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-042-01 | Configuration verification | SIT | Not Started
NFR-043 | Requirement | Non-Functional | E.5 Configurability & Extensibility | docs/scope/08-non-functional-requirements.md | RF workflow configuration: step order, optional/mandatory captures, prompts, and validations adjustable per site/owner/process through a flow designer. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-NFR-043-01 | Configuration verification | SIT | Not Started
NFR-044 | Requirement | Non-Functional | E.5 Configurability & Extensibility | docs/scope/08-non-functional-requirements.md | Extension points: (a) synchronous hooks (pre-/post-validation) as sandboxed serverless functions with ≤ 50 ms budget; (b) asynchronous event subscriptions; (c) custom REST endpoints under extension namespace. Extensions do not modify core code and survive upgrades. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-NFR-044-01 | Configuration verification | SIT | Not Started
NFR-045 | Requirement | Non-Functional | E.5 Configurability & Extensibility | docs/scope/08-non-functional-requirements.md | Label and document templates editable (ZPL / designer; HTML-to-PDF for documents), versioned per owner/customer. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-045-01 | Configuration verification | SIT | Not Started
NFR-046 | Requirement | Non-Functional | E.5 Configurability & Extensibility | docs/scope/08-non-functional-requirements.md | Localisation: UI in ≥ 12 languages, per-user language on RF; locale-aware numbers/dates/UoM; right-to-left capable. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-NFR-046-01 | Configuration verification | SIT | Not Started
NFR-047 | Requirement | Non-Functional | E.5 Configurability & Extensibility | docs/scope/08-non-functional-requirements.md | Upgrade cadence: continuous delivery with monthly feature releases; feature flags for opt-in behaviour changes; regulated tenants on quarterly validated release train. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-047-01 | Configuration verification | SIT | Not Started
NFR-060 | Requirement | Non-Functional | E.7 Logging & Audit Trails | docs/scope/08-non-functional-requirements.md | Business audit trail: every create/update/delete on master data, configuration, inventory, and orders records who, when (UTC + site local), from where (device/IP), what (before/after values), why (reason code), and via which channel (UI/RF/API/integration/job). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-060-01 | Security & audit | SIT; UAT | Not Started
NFR-061 | Requirement | Non-Functional | E.7 Logging & Audit Trails | docs/scope/08-non-functional-requirements.md | Audit trail is append-only and tamper-evident (hash-chained records per partition; periodic anchor hash stored in WORM storage). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-061-01 | Security & audit | SIT; UAT | Not Started
NFR-062 | Requirement | Non-Functional | E.7 Logging & Audit Trails | docs/scope/08-non-functional-requirements.md | Retention: inventory & financial-relevant audit ≥ 7 years (configurable up to 15); operational technical logs 90 days hot, 1 year archive. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-062-01 | Security & audit | SIT; UAT | Not Started
NFR-063 | Requirement | Non-Functional | E.7 Logging & Audit Trails | docs/scope/08-non-functional-requirements.md | Audit query UI and export (CSV/PDF) with filters; regulated tenants: audit review report for Part 11. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-063-01 | Security & audit | SIT; UAT | Not Started
NFR-064 | Requirement | Non-Functional | E.7 Logging & Audit Trails | docs/scope/08-non-functional-requirements.md | Technical logging: structured JSON logs, OpenTelemetry traces & metrics, centralised (customer-exportable); PII redaction in logs. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-064-01 | Security & audit | SIT; UAT | Not Started
NFR-065 | Requirement | Non-Functional | E.7 Logging & Audit Trails | docs/scope/08-non-functional-requirements.md | Configuration change log with diff and approver; emergency changes flagged. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-065-01 | Security & audit | SIT; UAT | Not Started
NFR-066 | Requirement | Non-Functional | E.7 Logging & Audit Trails | docs/scope/08-non-functional-requirements.md | Clock synchronisation: all services NTP-synchronised; timestamps in UTC ISO-8601 with ms precision. | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-066-01 | Security & audit | SIT; UAT | Not Started
NFR-080 | Requirement | Non-Functional | E.8 Usability & Operability | docs/scope/08-non-functional-requirements.md | RF task flows achievable with ≤ 1 keystroke per step on average (scan-driven); new operator productive after ≤ 4 h training for core tasks. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-NFR-080-01 | Usability | UAT | Not Started
NFR-081 | Requirement | Non-Functional | E.8 Usability & Operability | docs/scope/08-non-functional-requirements.md | Accessibility: web UI WCAG 2.2 AA. | Rule/requirement enforced as stated (positive + negative case) | S |  |  | TC-NFR-081-01 | Accessibility (WCAG 2.2 AA) | UAT | Not Started
NFR-082 | Requirement | Non-Functional | E.8 Usability & Operability | docs/scope/08-non-functional-requirements.md | Operability: runbooks for all alerts; SLO dashboards; synthetic transaction monitoring per site (RF login, task fetch, confirm). | Rule/requirement enforced as stated (positive + negative case) | M |  |  | TC-NFR-082-01 | Operability / production readiness | PERF | Not Started